## MS Project Import
CST238 SuccessFactors Programme - Level 4 Detailed Plan (sample)
Generated for demonstration purposes only - no real client data
ID | WBS | Outline Level | Task Name | Task Mode | Task Type | Milestone | Module | Track | Stage | Primary Owner | Resource Names | Party | Duration | Duration Days | Start | Finish | Predecessors | Constraint Type | Constraint Date | Deadline | Calendar | Deliverable | Acceptance Authority | Contract Reference | Critical Path | Baseline Confidence | Status | % Complete | Notes
1 | 1 | 1 | CST238 SuccessFactors Programme | Auto Scheduled | Summary | Programme | Programme | Programme | [9 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | High
2 | 1.1 | 2 | M1 - Programme Foundation | Auto Scheduled | Summary | M1 | Cross-functional | Programme | Prepare | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | High
3 | 1.1.1 | 3 | Programme kickoff workshop | Auto Scheduled | Task | M1 | Cross-functional | Programme | Prepare | Priya Menon | Priya Menon;Tom Reid | VE3 | 2d | 2 | 45901 | 45902 |  | As Soon As Possible |  |  | Standard | Signed kickoff minutes | Programme Board | SOW-1 | Yes | High | Complete | 100 | Well attended, all workstream leads present.
4 | 1.1.2 | 3 | Governance and RAID setup | Auto Scheduled | Task | M1 | Cross-functional | Programme | Prepare | Tom Reid | Tom Reid | Council | 3d | 3 | 45903 | 45905 | 3FS | As Soon As Possible |  |  | Standard | RAID log baselined | Programme Board | SOW-1 | No | High | Complete | 100
5 | 1.1.3 | 3 | Environment and tenant provisioning | Auto Scheduled | Task | M1 | Employee Central | Programme | Prepare | Dev Kapoor | Dev Kapoor | VE3 | 5d | 5 | 45903 | 45909 | 3FS | As Soon As Possible |  |  | Standard | Dev/test tenants live | Programme Board | SOW-1 | Yes | High | Complete | 100
6 | 1.1.4 | 3 | M1 acceptance | Auto Scheduled | Milestone | M1 | Programme | Programme | Prepare | Tom Reid | Tom Reid | Council | 0d | 0 | 45910 | 45910 | 4FS,5FS | As Soon As Possible |  |  | Standard | M1 signoff pack | Council Sponsor | SOW-1 | Yes | High | Complete | 100
7 | 1.2 | 2 | M2 - Explore Track A (Employee Central) | Auto Scheduled | Summary | M2 | Employee Central | Track A | Explore | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | Medium
8 | 1.2.1 | 3 | EC design workshops | Auto Scheduled | Task | M2 | Employee Central | Track A | Explore | Priya Menon | Priya Menon;Dev Kapoor | VE3 | 10d | 10 | 45911 | 45924 | 6FS | As Soon As Possible |  |  | Standard | EC design signoff | Programme Board | SOW-2 | Yes | Medium | Complete | 100
9 | 1.2.2 | 3 | Org structure and foundation objects design | Auto Scheduled | Task | M2 | Employee Central | Track A | Explore | Priya Menon | Priya Menon | Joint | 8d | 8 | 45925 | 45936 | 8FS | As Soon As Possible |  |  | Standard | FO design doc | Programme Board | SOW-2 | No | Medium | Complete | 100
10 | 1.2.3 | 3 | M2 acceptance | Auto Scheduled | Milestone | M2 | Programme | Track A | Explore | Priya Menon | Priya Menon | Council | 0d | 0 | 45937 | 45937 | 9FS | As Soon As Possible |  |  | Standard | M2 signoff pack | Council Sponsor | SOW-2 | Yes | Medium | Complete | 100
11 | 1.3 | 2 | M3 - Explore Track B (Recruiting / ECP) | Auto Scheduled | Summary | M3 | Recruiting | Track B | Explore | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | Medium
12 | 1.3.1 | 3 | Recruiting process design | Auto Scheduled | Task | M3 | Recruiting | Track B | Explore | Ravi Kaur | Ravi Kaur | Council | 9d | 9 | 45911 | 45923 | 6FS | As Soon As Possible |  |  | Standard | Recruiting design signoff | Programme Board | SOW-3 | No | Medium | Complete | 100
13 | 1.3.2 | 3 | ECP interface design | Auto Scheduled | Task | M3 | ECP | Track B | Explore | Dev Kapoor | Dev Kapoor;Ravi Kaur | Joint | 10d | 10 | 45924 | 45937 | 12FS | As Soon As Possible |  |  | Standard | ECP interface spec | Programme Board | SOW-3 | Yes | Medium | In Progress | 70 | Payroll vendor interface confirmed.
14 | 1.3.3 | 3 | M3 acceptance | Auto Scheduled | Milestone | M3 | Programme | Track B | Explore | Ravi Kaur | Ravi Kaur | Council | 0d | 0 | 45938 | 45938 | 13FS | As Soon As Possible |  |  | Standard | M3 signoff pack | Council Sponsor | SOW-3 | Yes | Medium | Not Started | 0
15 | 1.4 | 2 | M4 - Realize (Build) Track A | Auto Scheduled | Summary | M4 | Employee Central | Track A | Realize | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | Medium
16 | 1.4.1 | 3 | EC configuration build | Auto Scheduled | Task | M4 | Employee Central | Track A | Realize | Dev Kapoor | Dev Kapoor;Priya Menon | VE3 | 20d | 20 | 45939 | 45966 | 10FS | As Soon As Possible |  |  | Standard | Config in test tenant | Programme Board | SOW-2 | Yes | Medium | In Progress | 55
17 | 1.4.2 | 3 | Business rules and workflow configuration | Auto Scheduled | Task | M4 | Employee Central | Track A | Realize | Dev Kapoor | Dev Kapoor | VE3 | 10d | 10 | 45967 | 45980 | 16FS | As Soon As Possible |  |  | Standard | Rules signed off | Programme Board | SOW-2 | No | Medium | Not Started | 0
18 | 1.4.3 | 3 | Data migration dry run 1 | Auto Scheduled | Task | M4 | Employee Central | Track A | Realize | Priya Menon | Priya Menon | Joint | 5d | 5 | 45981 | 45987 | 17FS | As Soon As Possible |  |  | Standard | Dry run 1 report | Programme Board | SOW-2 | Yes | Low | Not Started | 0 | Depends on legacy extract availability - see AD-001.
19 | 1.4.4 | 3 | M4 acceptance | Auto Scheduled | Milestone | M4 | Programme | Track A | Realize | Dev Kapoor | Dev Kapoor | Council | 0d | 0 | 45988 | 45988 | 18FS | As Soon As Possible |  |  | Standard | M4 signoff pack | Council Sponsor | SOW-2 | Yes | Medium | Not Started | 0
20 | 1.5 | 2 | M5 - Realize (Build) Track B | Auto Scheduled | Summary | M5 | Recruiting | Track B | Realize | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | Medium
21 | 1.5.1 | 3 | Recruiting configuration build | Auto Scheduled | Task | M5 | Recruiting | Track B | Realize | Ravi Kaur | Ravi Kaur | Council | 15d | 15 | 45939 | 45959 | 14FS | As Soon As Possible |  |  | Standard | Config in test tenant | Programme Board | SOW-3 | No | Medium | Not Started | 0
22 | 1.5.2 | 3 | ECP integration build | Auto Scheduled | Task | M5 | ECP | Track B | Realize | Dev Kapoor | Dev Kapoor | Joint | 15d | 15 | 45960 | 45980 | 21FS | As Soon As Possible |  |  | Standard | Integration signed off | Programme Board | SOW-3 | Yes | Medium | Not Started | 0
23 | 1.5.3 | 3 | M5 acceptance | Auto Scheduled | Milestone | M5 | Programme | Track B | Realize | Ravi Kaur | Ravi Kaur | Council | 0d | 0 | 45981 | 45981 | 22FS | As Soon As Possible |  |  | Standard | M5 signoff pack (payment gate) | Council Sponsor | SOW-3 | Yes | Medium | Not Started | 0
24 | 1.6 | 2 | M6 - Deploy Preparation | Auto Scheduled | Summary | M6 | Cross-functional | Programme | Deploy | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | Medium
25 | 1.6.1 | 3 | UAT planning and scripting | Auto Scheduled | Task | M6 | Cross-functional | Programme | Deploy | Priya Menon | Priya Menon;Ravi Kaur | Joint | 8d | 8 | 45989 | 46000 | 19FS,23SS+5d | As Soon As Possible |  |  | Standard | UAT scripts signed off | Programme Board | SOW-1 | No | Medium | Not Started | 0
26 | 1.6.2 | 3 | User acceptance testing | Auto Scheduled | Task | M6 | Cross-functional | Programme | Deploy | Priya Menon | Priya Menon;Ravi Kaur;Dev Kapoor | Joint | 10d | 10 | 46001 | 46014 | 25FS | As Soon As Possible |  |  | Standard | UAT signoff | Programme Board | SOW-1 | Yes | Medium | Not Started | 0
27 | 1.6.3 | 3 | M6 acceptance | Auto Scheduled | Milestone | M6 | Programme | Programme | Deploy | Tom Reid | Tom Reid | Council | 0d | 0 | 46015 | 46015 | 26FS | As Soon As Possible |  |  | Standard | M6 signoff pack | Council Sponsor | SOW-1 | Yes | Medium | Not Started | 0
28 | 1.7 | 2 | M7 - Go-Live and Cutover | Auto Scheduled | Summary | M7 | Cross-functional | Programme | Deploy | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | Medium
29 | 1.7.1 | 3 | Cutover rehearsal | Auto Scheduled | Task | M7 | Cross-functional | Programme | Deploy | Dev Kapoor | Dev Kapoor | VE3 | 3d | 3 | 46027 | 46029 | 27FS | As Soon As Possible |  |  | Standard | Cutover rehearsal report | Programme Board | SOW-1 | Yes | Medium | Not Started | 0
30 | 1.7.2 | 3 | Production data migration and go-live | Auto Scheduled | Task | M7 | Cross-functional | Programme | Deploy | Dev Kapoor | Dev Kapoor;Priya Menon | Joint | 4d | 4 | 46030 | 46033 | 29FS | As Soon As Possible |  |  | Standard | Go-live signoff | Programme Board | SOW-1 | Yes | Medium | Not Started | 0
31 | 1.7.3 | 3 | M7 acceptance | Auto Scheduled | Milestone | M7 | Programme | Programme | Deploy | Tom Reid | Tom Reid | Council | 0d | 0 | 46034 | 46034 | 30FS | As Soon As Possible |  |  | Standard | M7 signoff pack | Council Sponsor | SOW-1 | Yes | Medium | Not Started | 0
32 | 1.8 | 2 | M8 - Hypercare | Auto Scheduled | Summary | M8 | Cross-functional | Programme | Run | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | Medium
33 | 1.8.1 | 3 | Hypercare support | Auto Scheduled | Task | M8 | Cross-functional | Programme | Run | Priya Menon | Priya Menon;Dev Kapoor;Ravi Kaur | Joint | 15d | 15 | 46035 | 46055 | 31FS | As Soon As Possible |  |  | Standard | Hypercare log clean | Programme Board | SOW-1 | No | Medium | Not Started | 0
34 | 1.8.2 | 3 | M8 acceptance | Auto Scheduled | Milestone | M8 | Programme | Programme | Run | Tom Reid | Tom Reid | Council | 0d | 0 | 46056 | 46056 | 33FS | As Soon As Possible |  |  | Standard | Hypercare exit report | Council Sponsor | SOW-1 | No | Medium | Not Started | 0
35 | 1.9 | 2 | M9 - Programme Closure | Auto Scheduled | Summary | M9 | Cross-functional | Programme | Run | [8 empty] | As Soon As Possible |  |  | Standard |  |  |  | No | Medium | Medium
36 | 1.9.1 | 3 | Lessons learned and closure report | Auto Scheduled | Task | M9 | Cross-functional | Programme | Run | Tom Reid | Tom Reid | Joint | 5d | 5 | 46057 | 46063 | 34FS | As Soon As Possible |  |  | Standard | Closure report | Programme Board | SOW-1 | No | Medium | Not Started | 0
37 | 1.9.2 | 3 | M9 - Final acceptance | Auto Scheduled | Milestone | M9 | Programme | Programme | Run | Tom Reid | Tom Reid | Council | 0d | 0 | 46064 | 46064 | 36FS | As Soon As Possible |  |  | Standard | Final signoff and contract closure | Council Sponsor | SOW-1 | Yes | Medium | Not Started | 0

## Milestone Summary
Milestone | Contract Stage / Track | Planning Target | Contract Timing | Payment % | Acceptance Authority | Acceptance Evidence | Executable Tasks | Critical Tasks | Baseline Confidence | Schedule Status | Source | Comment
M1 | Prepare / Programme | 45910 | Contractual | 0.1 | Council Sponsor | M1 signoff pack | 4 | 2 | High | Complete | Contract Schedule 2
M2 | Explore / Track A | 45937 | Contractual | 0.1 | Council Sponsor | M2 signoff pack | 3 | 1 | High | Complete | Contract Schedule 2
M3 | Explore / Track B | 45938 | Contractual | 0.1 | Council Sponsor | M3 signoff pack | 3 | 2 | Medium | In Progress | Contract Schedule 2 | ECP interface design running to plan.
M4 | Realize / Track A | 45988 | Contractual | 0.15 | Council Sponsor | M4 signoff pack | 4 | 2 | Medium | In Progress | Contract Schedule 2 | Watch data migration dry run - see AD-001.
M5 | Realize / Track B | 45981 | Contractual | 0.15 | Council Sponsor | M5 signoff pack | 3 | 2 | Medium | Not Started | Contract Schedule 2 | Payment gate - 15%.
M6 | Deploy prep | 46015 | Contractual | 0.1 | Council Sponsor | M6 signoff pack | 3 | 1 | Medium | Not Started | Contract Schedule 2
M7 | Go-live | 46034 | Contractual | 0.15 | Council Sponsor | M7 signoff pack | 3 | 3 | Medium | Not Started | Contract Schedule 2 | Payment gate - 15%.
M8 | Hypercare | 46056 | Contractual | 0.05 | Council Sponsor | Hypercare exit report | 2 | 0 | Medium | Not Started | Contract Schedule 2
M9 | Programme close | 46064 | Contractual | 0.1 | Council Sponsor | Final signoff | 2 | 1 | Medium | Not Started | Contract Schedule 2

## Resource Dictionary
Resource / Role | Organisation
Priya Menon | VE3
Dev Kapoor | VE3
Tom Reid | Council
Ravi Kaur | Council

## Assumptions Decisions
ID | Type | Topic | Current Planning Position | Impact if Wrong | Decision / Evidence Required | Owner | Target Decision Date | Status | Affects Milestone | Schedule Treatment | Source | MD Attention
AD-001 | Risk | Legacy data extract availability | Council to provide clean extract by mid-Nov | 2-3 week slip to M4 data migration | Confirm extract format and delivery date with Council data team | Priya Menon | 45964 | Open | M4 | Monitor closely | Workshop notes 12 Sep | High
AD-002 | Assumption | ECP vendor interface spec | Payroll vendor confirmed API v3 | Rework of interface build if vendor changes spec | Written confirmation from vendor account manager | Dev Kapoor | 45931 | Open | M3 | No change | Vendor call 20 Sep | Medium
AD-003 | Decision | UAT entry criteria | All M4/M5 critical tasks must be Complete before UAT starts | UAT start slips if Realize phase runs long | Programme Board to ratify entry criteria | Tom Reid | 45976 | Open | M6 | Gate on completion | Governance charter | Medium

## MD Brief
Baseline Outcome | Value | Executive Implication | Control
M1 and M2 delivered on time and on budget | Low risk | No MD action needed this period | Monitor weekly programme board pack
M3 (Track B) running two days behind micro-plan | Low-medium risk | No milestone date impact expected yet | Weekly Track B stand-up added
Legacy data extract (AD-001) still unconfirmed | Medium risk to M4 | May need MD sponsorship to unblock Council data team | Escalate if unresolved by 3 Nov
MD Priority | Detail
Confirm Council data extract timeline (AD-001) before 3 Nov | Unblocks M4 data migration dry run; owner Priya Menon
Ratify UAT entry criteria at next Programme Board | Needed to protect M6 date; owner Tom Reid
Sponsor decision on ECP vendor interface spec (AD-002) | Avoids rework risk on M3/M5 ECP build

## Import Guide
Import Guide
This is a synthetic sample workbook shipped with the L4 Programme Plan Viewer for demonstration only.
It follows the same column layout the app expects from a real MS Project L4 export - see the app README for the full column reference.